## Harrison_George
Staff Planning
Staff Name: | Harrison, George
PROJECT | FUNDING | PROJECT | MANAGER or | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
NUMBER | PROBABILITY | DESCRIPTION | TASK MANAGER | Total
|  |  | Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026
|  |  | Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25
84392 | 0.8 | Meet the Beatles! | None | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96
65557 | 0.2 | Twist and Shout | None | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96
59534 | 1 | Please Please Me | None | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013
68344 | 0.5 | With the Beatles | None | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013
74589 | 0.2 | A Hard Days Night | None | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96

## Lennon_John
Staff Planning
Staff Name: | Lennon, John
PROJECT | FUNDING | PROJECT | MANAGER or | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
NUMBER | PROBABILITY | DESCRIPTION | TASK MANAGER | Total
|  |  | Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026
|  |  | Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25
84392 | 0.8 | Meet the Beatles! | None | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013
22536 | 1 | Introducing … the Beatles | None | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013
65557 | 0.2 | Twist and Shout | None | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24
74589 | 0.2 | A Hard Days Night | None | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24

## McCartney_Paul
Staff Planning
Staff Name: | McCartney, Paul
PROJECT | FUNDING | PROJECT | MANAGER or | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
NUMBER | PROBABILITY | DESCRIPTION | TASK MANAGER | Total
|  |  | Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026
|  |  | Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25
84392 | 0.8 | Meet the Beatles! | None | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 20
65557 | 0.2 | Twist and Shout | None | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013
83332 | 1 | The Beatles Second Album | None | 5 | 5 | 5 | 5 | 5 | 5 | 100 | 5 | 5 | 5 | 5 | 5 | 155
22567 | 0.45 | Beatles for Sale | None | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60

## Starr_Ringo
Staff Planning
Staff Name: | Starr, Ringo
PROJECT | FUNDING | PROJECT | MANAGER or | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
NUMBER | PROBABILITY | DESCRIPTION | TASK MANAGER | Total
|  |  | Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026
|  |  | Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25
84392 | 0.8 | Meet the Beatles! | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
22536 | 1 | Introducing … the Beatles | None | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 45
65557 | 0.2 | Twist and Shout | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
83332 | 1 | The Beatles Second Album | None | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 100 | 4 | 4 | 0 | 141
74589 | 0.2 | A Hard Days Night | None | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013
22567 | 0.45 | Beatles for Sale | None | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 40 | 40 | 121