## 74589
Project Labor Planning
1a. Project Number:* | 74589 |  | 1b. Proposal Number:* |  |  |  | 1c. WP#(s)/Task/WBS:*
2. Title: | A Hard Days Night
3. Client: | United Artists
4. Start & End Dates: |  | through
5. Funding amount:
6. Probability %: | 20
7. Manager: | None
8. Comments (optional):
*Fill in either 1a. for a current project with funding; 1b. for a proposal that has not been funded/awarded yet; or 1c. for wp#(s), a task, or WBS that is funded from outside your group. If this is a proposal (1b), please enter teh probability % of being funded/awarded in #6 above.
Group Staff | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
| Jan-18 | Feb-18 | Mar-18 | Apr-18 | May-18 | Jun-18 | Jul-18 | Aug-18 | Sep-18 | Oct-18 | Nov-18 | Dec-18 | Total | % of Available Hours Covered
Wkg Hrs Available = | 152 | 160 | 200 | 160 | 160 | 192 | 152 | 200 | 192 | 136 | 120 | 136 | 1960
Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sept 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25
Harrison, George | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 4.898%
Lennon, John | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 1.224%
McCartney, Paul | [12 empty] | 0 | 0%
Starr, Ringo | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013 | 51.68%
Total | 98 | 90 | 90 | 90 | 106 | 90 | 87 | 110 | 110 | 90 | 82 | 90 | 1133

## 22567
Project Labor Planning
1a. Project Number:* | 22567 |  | 1b. Proposal Number:* |  |  |  | 1c. WP#(s)/Task/WBS:*
2. Title: | Beatles for Sale
3. Client: | Parlophone
4. Start & End Dates: |  | through
5. Funding amount:
6. Probability %: | 45
7. Manager: | None
8. Comments (optional):
*Fill in either 1a. for a current project with funding; 1b. for a proposal that has not been funded/awarded yet; or 1c. for wp#(s), a task, or WBS that is funded from outside your group. If this is a proposal (1b), please enter teh probability % of being funded/awarded in #6 above.
Group Staff | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
| Jan-18 | Feb-18 | Mar-18 | Apr-18 | May-18 | Jun-18 | Jul-18 | Aug-18 | Sep-18 | Oct-18 | Nov-18 | Dec-18 | Total | % of Available Hours Covered
Wkg Hrs Available = | 152 | 160 | 200 | 160 | 160 | 192 | 152 | 200 | 192 | 136 | 120 | 136 | 1960
Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sept 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25
Harrison, George | [12 empty] | 0 | 0%
Lennon, John | [12 empty] | 0 | 0%
McCartney, Paul | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60 | 3.061%
Starr, Ringo | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 40 | 40 | 121 | 6.173%
Total | 9 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 45 | 45 | 181