## sheet_0
Staff Planning
Project Rollup
Project ID: | 59534
Project Title: | Please Please Me
Project Manager: | None
Funding Probability: | 1
Technical Group | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026 | Percent Covered
Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25 | Dec 27, 2018 - Dec 25, 2019
Harrison_George | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013 | 50%

## sheet_1
Staff Planning
Project Rollup
Project ID: | 68344
Project Title: | With the Beatles
Project Manager: | None
Funding Probability: | 0.5
Technical Group | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026 | Percent Covered
Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25 | Dec 27, 2018 - Dec 25, 2019
Harrison_George | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013 | 50%

## sheet_2
Staff Planning
Project Rollup
Project ID: | 84392
Project Title: | Meet the Beatles!
Project Manager: | None
Funding Probability: | 0.8
Technical Group | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026 | Percent Covered
Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25 | Dec 27, 2018 - Dec 25, 2019
Harrison_George | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 4.738%
Lennon_John | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013 | 50%
McCartney_Paul | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 20 | 0.9872%
Starr_Ringo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 0.1974%

## sheet_3
Staff Planning
Project Rollup
Project ID: | 65557
Project Title: | Twist and Shout
Project Manager: | None
Funding Probability: | 0.2
Technical Group | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026 | Percent Covered
Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25 | Dec 27, 2018 - Dec 25, 2019
Harrison_George | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 4.738%
Lennon_John | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 1.185%
McCartney_Paul | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013 | 50%
Starr_Ringo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 0.1974%

## sheet_4
Staff Planning
Project Rollup
Project ID: | 74589
Project Title: | A Hard Days Night
Project Manager: | None
Funding Probability: | 0.2
Technical Group | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026 | Percent Covered
Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25 | Dec 27, 2018 - Dec 25, 2019
Harrison_George | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 4.738%
Lennon_John | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 1.185%
Starr_Ringo | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013 | 50%

## sheet_5
Staff Planning
Project Rollup
Project ID: | 22536
Project Title: | Introducing … the Beatles
Project Manager: | None
Funding Probability: | 1
Technical Group | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026 | Percent Covered
Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25 | Dec 27, 2018 - Dec 25, 2019
Lennon_John | 88 | 80 | 80 | 80 | 96 | 80 | 77 | 100 | 100 | 80 | 72 | 80 | 1013 | 50%
Starr_Ringo | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 45 | 2.221%

## sheet_6
Staff Planning
Project Rollup
Project ID: | 83332
Project Title: | The Beatles Second Album
Project Manager: | None
Funding Probability: | 1
Technical Group | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026 | Percent Covered
Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25 | Dec 27, 2018 - Dec 25, 2019
McCartney_Paul | 5 | 5 | 5 | 5 | 5 | 5 | 100 | 5 | 5 | 5 | 5 | 5 | 155 | 7.651%
Starr_Ringo | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 100 | 4 | 4 | 0 | 141 | 6.96%

## sheet_7
Staff Planning
Project Rollup
Project ID: | 22567
Project Title: | Beatles for Sale
Project Manager: | None
Funding Probability: | 0.45
Technical Group | Quarter 2 - FY18 |  |  | Quarter 3 - FY18 |  |  | Quarter 4 - FY18 |  |  | Quarter 1 - FY19
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
Wkg Hrs Available = | 176 | 160 | 160 | 160 | 192 | 160 | 154 | 200 | 200 | 160 | 144 | 160 | 2026 | Percent Covered
Processing Month = | Dec 27-Jan 23 | Jan 24-Feb 20 | Feb 21-Mar 27 | Mar 28-Apr 24 | Apr 25-May 22 | May 23-Jun 26 | Jun 27-Jul 24 | Jul 25-Aug 21 | Aug 22-Sep 30 | Oct 1-Oct 23 | Oct 24-Nov 20 | Nov 21-Dec 25 | Dec 27, 2018 - Dec 25, 2019
McCartney_Paul | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60 | 2.962%
Starr_Ringo | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 40 | 40 | 121 | 5.972%